## Gantt
Project Plan - Gantt Chart
ID | Week | Task | Role | Start | End | Deliverable | W1 | W2 | W3 | W4 | W5 | W6 | W7
1 | 1 | KPI Specification and KPIs Document | Hossam - Technical Analytics Lead | 2026-10-11 | 2026-10-15 | KPI Specification + KPIs Document
2 | 1 | GitHub Repository and Branching Strategy | Hossam - Technical Analytics Lead | 2026-10-11 | 2026-10-15 | Repository + Branching Strategy
3 | 1 | Raw and Working Data Layers with Data Profiling | Yahia - Data Preparation & Testing Lead | 2026-10-11 | 2026-10-15 | Raw/Working Data Layers + Profiling Report
4 | 1 | Project Plan and Task Assignment | Hossam - Technical Analytics Lead | 2026-10-11 | 2026-10-15 | Project Plan + Task Assignment & Roles
5 | 1 | Project Proposal | Hossam - Technical Analytics Lead | 2026-10-11 | 2026-10-15 | Project Proposal
6 | 1 | Stakeholder Analysis and User Stories & Use Cases | Ola - Data Quality & Review Lead | 2026-10-11 | 2026-10-15 | Stakeholder Analysis + User Stories & Use Cases
7 | 1 | Literature Review File (Lecturer Input) | Ola - Data Quality & Review Lead | 2026-10-11 | 2026-10-15 | Literature Review
8 | 1 | Data Dictionary | Aya - Data Dictionary & Requirements Lead | 2026-10-11 | 2026-10-15 | Validated Data Dictionary
9 | 1 | Functional & Non-functional Requirements | Aya - Data Dictionary & Requirements Lead | 2026-10-11 | 2026-10-15 | Functional & Non-functional Requirements
10 | 1 | Risk Assessment & Mitigation Plan | Aya - Data Dictionary & Requirements Lead | 2026-10-11 | 2026-10-15 | Risk Assessment & Mitigation Plan
11 | 2 | SQL Staging, Duplicate and Key Integrity Checks | Hossam - Technical Analytics Lead | 2026-10-18 | 2026-10-22 | SQL Staging Layer + Integrity Report
12 | 2 | Shipments Table Cleaning | Yahia - Data Preparation & Testing Lead | 2026-10-18 | 2026-10-22 | Clean Shipments Table + Cleaning Log
13 | 2 | Hospital Tables Cleaning | Yahia - Data Preparation & Testing Lead | 2026-10-18 | 2026-10-22 | Clean Hospital Tables + Cleaning Log
14 | 2 | Data Quality Rules and Mapping Sign-off | Ola - Data Quality & Review Lead | 2026-10-18 | 2026-10-22 | Data Quality Rules + Categorical Mapping Sign-off
15 | 2 | Before/After Reconciliation | Aya - Data Dictionary & Requirements Lead | 2026-10-18 | 2026-10-22 | Before/After Reconciliation Report
16 | 3 | Python Notebook: KPI Recalculation, Basic Charts and Statistical Analysis | Hossam - Technical Analytics Lead | 2026-10-25 | 2026-10-29 | Python Notebook (pandas, matplotlib, SciPy, statsmodels) + Statistical Results Table
17 | 3 | Derived Fields and Cleaned Dataset | Yahia - Data Preparation & Testing Lead | 2026-10-25 | 2026-10-29 | Derived Fields + Cleaned Dataset
18 | 3 | Question-to-KPI-to-Chart Map | Ola - Data Quality & Review Lead | 2026-10-25 | 2026-10-29 | Analytical Question Map
19 | 3 | Wireframes & UI/UX Guidelines | Aya - Data Dictionary & Requirements Lead | 2026-10-25 | 2026-10-29 | Dashboard UX Specification (Wireframes + Guidelines)
20 | 4 | Software Architecture, DFD and Technology Stack | Hossam - Technical Analytics Lead | 2026-11-01 | 2026-11-05 | Software Architecture + DFD + Technology Stack
21 | 4 | Power BI Data Models (Shipments and Hospitals, Kept Separate) and Core Measures | Yahia - Data Preparation & Testing Lead | 2026-11-01 | 2026-11-05 | Validated Data Models + Core Measures
22 | 4 | Problem Statement and Use Case Diagram | Ola - Data Quality & Review Lead | 2026-11-01 | 2026-11-05 | Problem Statement + Use Case Diagram
23 | 4 | ER Diagram and Logical & Physical Schema | Aya - Data Dictionary & Requirements Lead | 2026-11-01 | 2026-11-05 | ER Diagram + Logical & Physical Schema
24 | 5 | Dashboard Page 1: Executive Overview | Ola - Data Quality & Review Lead | 2026-11-08 | 2026-11-12 | Dashboard Page 1
25 | 5 | Dashboard Page 2: Delivery & Cycle Time | Hossam - Technical Analytics Lead | 2026-11-08 | 2026-11-12 | Dashboard Page 2
26 | 5 | Dashboard Page 3: Suppliers & Cost | Aya - Data Dictionary & Requirements Lead | 2026-11-08 | 2026-11-12 | Dashboard Page 3
27 | 5 | Dashboard Page 4: Purchase Orders & Inventory | Yahia - Data Preparation & Testing Lead | 2026-11-08 | 2026-11-12 | Dashboard Page 4
28 | 5 | Dashboard Page 5: Case Impact & Decision Quality | Hossam - Technical Analytics Lead | 2026-11-08 | 2026-11-12 | Dashboard Page 5
29 | 6 | Master Reconciliation (SQL, Python, Power BI) | Hossam - Technical Analytics Lead | 2026-11-15 | 2026-11-19 | Master Reconciliation Report
30 | 6 | Test Plan, Functional Testing, UAT and Bug Log | Yahia - Data Preparation & Testing Lead | 2026-11-15 | 2026-11-19 | Test Plan + Dashboard Functional Test + UAT & Bug Log
31 | 6 | Findings and Recommendations | Ola - Data Quality & Review Lead | 2026-11-15 | 2026-11-19 | Findings & Recommendations
32 | 6 | README and Execution Guide | Aya - Data Dictionary & Requirements Lead | 2026-11-15 | 2026-11-19 | README + Execution Guide
33 | 7 | Technical Sign-off and Final Refresh QA | Hossam - Technical Analytics Lead | 2026-11-22 | 2026-11-26 | Technical Sign-off Package + Final Refresh QA
34 | 7 | Project Infographic (Single 16:9 Image) | Yahia - Data Preparation & Testing Lead | 2026-11-22 | 2026-11-26 | Project Infographic
35 | 7 | Project Presentation (PPT/PDF) | Ola - Data Quality & Review Lead | 2026-11-22 | 2026-11-26 | Project Presentation
36 | 7 | User Manual and Final Documentation | Aya - Data Dictionary & Requirements Lead | 2026-11-22 | 2026-11-26 | User Manual + Final Documentation

## Milestones
Project Plan - Milestones
Milestone | Date | Focus | Exit Gate
Week 1 end | 2026-10-15 | Scope, Definitions, Raw/Working Layers and Planning Documents | Planning, literature review and requirements documents are ready for submission on 16 October 2026.
Week 2 end | 2026-10-22 | Data Cleaning, Integrity Checks and Quality Rules | Cleaning logs and documented mappings are delivered; before/after differences are explained.
Week 3 end | 2026-10-29 | Derived Fields, Cleaned Dataset, Python Notebook (KPI Recalculation, Basic Charts and Statistical Analysis) and Dashboard Design | Derived fields are validated and the analytical question map is agreed.
Week 4 end | 2026-11-05 | System Analysis & Design Pack and Power BI Data Models | Design documents are ready for submission on 6 November 2026; relationships, denominators and filters are tested.
Week 5 end | 2026-11-12 | Dashboard Build: Five Pages | Every visual is linked to a specific question, column and KPI.
Week 6 end | 2026-11-19 | Reconciliation, Testing, UAT and Findings | No critical error remains open.
Week 7 end | 2026-11-26 | Sign-off, Infographic, Presentation and Final Documentation | Final internal delivery.
DEPI Submission | Date | Item
DEPI submission | 2026-10-16 | Project Planning & Management | Documents uploaded to GitHub
DEPI submission | 2026-10-16 | Literature Review | Documents uploaded to GitHub
DEPI submission | 2026-10-16 | Requirements Gathering | Documents uploaded to GitHub
DEPI submission | 2026-11-06 | System Analysis & Design | Documents uploaded to GitHub
DEPI submission | 2026-11-30 | Implementation (Source Code & Execution) | Documents uploaded to GitHub
DEPI submission | 2026-12-04 | Final Presentation, Testing & Reports | Documents uploaded to GitHub
Internal final delivery | 2026-11-26 | Final internal delivery (Week 7 end) | Final internal delivery

## Deliverables
Project Plan - Deliverables
Task ID | Deliverable | Role | Week | Due Date
1 | KPI Specification + KPIs Document | Hossam - Technical Analytics Lead | 1 | 2026-10-15
2 | Repository + Branching Strategy | Hossam - Technical Analytics Lead | 1 | 2026-10-15
3 | Raw/Working Data Layers + Profiling Report | Yahia - Data Preparation & Testing Lead | 1 | 2026-10-15
4 | Project Plan + Task Assignment & Roles | Hossam - Technical Analytics Lead | 1 | 2026-10-15
5 | Project Proposal | Hossam - Technical Analytics Lead | 1 | 2026-10-15
6 | Stakeholder Analysis + User Stories & Use Cases | Ola - Data Quality & Review Lead | 1 | 2026-10-15
7 | Literature Review | Ola - Data Quality & Review Lead | 1 | 2026-10-15
8 | Validated Data Dictionary | Aya - Data Dictionary & Requirements Lead | 1 | 2026-10-15
9 | Functional & Non-functional Requirements | Aya - Data Dictionary & Requirements Lead | 1 | 2026-10-15
10 | Risk Assessment & Mitigation Plan | Aya - Data Dictionary & Requirements Lead | 1 | 2026-10-15
11 | SQL Staging Layer + Integrity Report | Hossam - Technical Analytics Lead | 2 | 2026-10-22
12 | Clean Shipments Table + Cleaning Log | Yahia - Data Preparation & Testing Lead | 2 | 2026-10-22
13 | Clean Hospital Tables + Cleaning Log | Yahia - Data Preparation & Testing Lead | 2 | 2026-10-22
14 | Data Quality Rules + Categorical Mapping Sign-off | Ola - Data Quality & Review Lead | 2 | 2026-10-22
15 | Before/After Reconciliation Report | Aya - Data Dictionary & Requirements Lead | 2 | 2026-10-22
16 | Python Notebook (pandas, matplotlib, SciPy, statsmodels) + Statistical Results Table | Hossam - Technical Analytics Lead | 3 | 2026-10-29
17 | Derived Fields + Cleaned Dataset | Yahia - Data Preparation & Testing Lead | 3 | 2026-10-29
18 | Analytical Question Map | Ola - Data Quality & Review Lead | 3 | 2026-10-29
19 | Dashboard UX Specification (Wireframes + Guidelines) | Aya - Data Dictionary & Requirements Lead | 3 | 2026-10-29
20 | Software Architecture + DFD + Technology Stack | Hossam - Technical Analytics Lead | 4 | 2026-11-05
21 | Validated Data Models + Core Measures | Yahia - Data Preparation & Testing Lead | 4 | 2026-11-05
22 | Problem Statement + Use Case Diagram | Ola - Data Quality & Review Lead | 4 | 2026-11-05
23 | ER Diagram + Logical & Physical Schema | Aya - Data Dictionary & Requirements Lead | 4 | 2026-11-05
24 | Dashboard Page 1 | Ola - Data Quality & Review Lead | 5 | 2026-11-12
25 | Dashboard Page 2 | Hossam - Technical Analytics Lead | 5 | 2026-11-12
26 | Dashboard Page 3 | Aya - Data Dictionary & Requirements Lead | 5 | 2026-11-12
27 | Dashboard Page 4 | Yahia - Data Preparation & Testing Lead | 5 | 2026-11-12
28 | Dashboard Page 5 | Hossam - Technical Analytics Lead | 5 | 2026-11-12
29 | Master Reconciliation Report | Hossam - Technical Analytics Lead | 6 | 2026-11-19
30 | Test Plan + Dashboard Functional Test + UAT & Bug Log | Yahia - Data Preparation & Testing Lead | 6 | 2026-11-19
31 | Findings & Recommendations | Ola - Data Quality & Review Lead | 6 | 2026-11-19
32 | README + Execution Guide | Aya - Data Dictionary & Requirements Lead | 6 | 2026-11-19
33 | Technical Sign-off Package + Final Refresh QA | Hossam - Technical Analytics Lead | 7 | 2026-11-26
34 | Project Infographic | Yahia - Data Preparation & Testing Lead | 7 | 2026-11-26
35 | Project Presentation | Ola - Data Quality & Review Lead | 7 | 2026-11-26
36 | User Manual + Final Documentation | Aya - Data Dictionary & Requirements Lead | 7 | 2026-11-26

## Resource Allocation
Project Plan - Resource Allocation
Role | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Total Tasks
Hossam - Technical Analytics Lead | 4 | 1 | 1 | 1 | 2 | 1 | 1 | 11
Yahia - Data Preparation & Testing Lead | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 8
Ola - Data Quality & Review Lead | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 8
Aya - Data Dictionary & Requirements Lead | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 9
Total | 10 | 5 | 4 | 4 | 5 | 4 | 4 | 36
Role | Responsibilities
Hossam - Technical Analytics Lead | Project proposal; project plan and task assignment; KPI specification and KPIs document; GitHub repository; SQL staging and integrity checks; Python notebook (KPI recalculation, basic charts and statistical analysis); software architecture, DFD and technology stack; dashboard Pages 2 (Delivery & Cycle Time) and 5 (Case Impact & Decision Quality); master reconciliation; technical sign-off and final refresh QA.
Yahia - Data Preparation & Testing Lead | Raw and Working data layers with profiling; cleaning of the shipments and hospital tables; derived fields and cleaned dataset; Power BI data models and core measures; dashboard Page 4 (Purchase Orders & Inventory); test plan, UAT and bug log; project infographic.
Ola - Data Quality & Review Lead | Stakeholder analysis, user stories and use cases; literature review file; data quality rules and mapping sign-off; analytical question map; problem statement and use case diagram; dashboard Page 1 (Executive Overview); findings and recommendations; project presentation.
Aya - Data Dictionary & Requirements Lead | Data dictionary; functional and non-functional requirements; risk assessment; before/after reconciliation; wireframes and UI/UX guidelines; ER diagram and logical & physical schema; dashboard Page 3 (Suppliers & Cost); README and execution guide; user manual and final documentation.

## Python Statistical Analysis
Project Plan - Python Statistical Analysis (Task 16)
Part of Task 16 (Hossam - Technical Analytics Lead), Week 3 (25-29 October 2026). Libraries: pandas and NumPy (data handling), SciPy (scipy.stats: statistical tests), statsmodels (confidence intervals, multiple-comparison correction, stratified tables), matplotlib (charts). Run the steps in order S0 to S17 in one notebook.
Step | Question(s) | Analysis | Input (table: columns) | Valid rows and expected sample size | Method and library function | Output | Limit of interpretation
S0 | All | Setup and guard rules | Cleaned shipments table (sheet in) and cleaned hospital tables (inventory_daily, purchase_orders, patient_cases) with their cleaning flags; items, suppliers, hospitals. | Valid-row definitions exactly as in the approved Data Quality Rules (Scope Rules, section D): PO Delay and PO On-Time 1,962 rows; Stockout Rate 8,926 rows; Lead Time 45 rows; Freight per Kg 38 rows; Late Rate 46 rows. Each test drops only rows that are NULL in its own columns and records the excluded count. | pandas (read, merge, groupby, dropna per test); NumPy; scipy.stats.shapiro (n up to 5,000) and scipy.stats.skew for the distribution check; statsmodels.stats.multitest.multipletests(method="holm") for every family of comparisons. Significance level 0.05 (documented assumption). Minimum group size: 5 shipments per country and 3 per vendor (project rules); MIN_N = 30 rows or cases for hospital-layer groups (documented assumption, one constant confirmed in the Question Map, Task 18). | Results table stats_results with columns: step, question, n_valid, n_excluded, method, statistic, p_value, p_holm, effect_size, ci_low, ci_high. | A blank stays NULL and is never converted to zero; no value is deleted because it is large; every p-value is shown with n, an effect size and a 95% confidence interval.
S1 | Q04, Q05, Q07, Q11 | Descriptive statistics of the shipment KPIs | in: scheduled delivery date, delivered to client date, po sent to vendor date, delivery recorded date, expiry_date, freight cost (usd), weight (kilograms). | Delay Days on 46 rows (0 late, 44 on schedule, 2 early); Lead Time Days on 45 rows; Shelf Life at Delivery on rows with a valid expiry_date (43 valid dates in the source); Freight per Kg on 38 rows. | pandas describe and quantile (median, IQR, P90); scipy.stats.skew; statsmodels.stats.proportion.proportion_confint(method="wilson") for the schedule-status shares. | Summary table per KPI with n; histograms with the IQR-rule outlier check (matplotlib). | No shipment is late, so no inferential test is run on Delay Days; median 0 means no late shipment exists in the sample, not "no delay".
S2 | Q05 | Lead time by country | in: country (standardized to country_clean), Lead Time Days. | Countries with at least 5 valid lead times: Nigeria 17, Haiti 7, Cote d'Ivoire 6, Congo DRC 6, Guyana 5; Afghanistan (3) and Ethiopia (1) are grouped as Other (calculated from the source). | scipy.stats.kruskal across the five countries; effect size epsilon-squared = (H - k + 1) / (n - k); pairwise scipy.stats.mannwhitneyu with Holm correction. | Median [IQR] and n per country; test table; box plot. | Groups are small (5 to 17), so the result is exploratory; differences between countries are not explained by this test.
S3 | Q06 | Customs clearance days against lead time | in: customs_clearance_days (after standardization: "3 days" becomes 3 and "~6" becomes 6 with an approximate flag), Lead Time Days. | Rows where both values are valid: 44 (45 valid lead times and 45 valid customs values in the source). | scipy.stats.spearmanr; 95% interval with scipy.stats.bootstrap (paired resampling, 10,000 resamples, seed 42); sensitivity run without the approximate-flag rows; median of customs_clearance_days / Lead Time Days as the share of cycle time spent in customs. | Spearman rho, p-value, interval, sensitivity result, median customs share; scatter plot. | Correlation is not cause; the relation is stated with its sample size.
S4 | Q07 | Shelf life at delivery and receiving inspection | in: expiry_date, delivered to client date, receiving_inspection_result (raw variants mapped first). | Shelf Life on rows with a valid expiry date (43 in the source); inspection acceptance on rows with a non-blank result, blanks excluded and counted. | pandas; statsmodels.stats.proportion.proportion_confint(method="wilson") for the share expired on arrival and for the Inspection Acceptance Rate; scipy.stats.skew. | Shelf-life histogram, inspection donut data, table of shipments expired on arrival. | Negative shelf life is listed for review, not deleted; shares are shown with n.
S5 | Q08 | Vendor concentration | in: vendor, line item value. | All 46 rows (line item value is never missing); vendors with fewer than 3 shipments are grouped as Other. | pandas groupby and cumulative share (Pareto); NumPy for the Herfindahl-Hirschman Index = sum of squared vendor value shares. | Pareto table, HHI value. | Descriptive concentration measure only; no vendor is ranked below the minimum size.
S6 | Q10, Q11 | Freight against weight and cost efficiency | in: freight cost (usd), weight (kilograms), line item value, line item insurance (usd). | Freight per Kg and the relation between freight and weight on the 38 rows where both are numeric; Freight/Value = SUM(freight) / SUM(value) on the rows where freight is numeric. | scipy.stats.spearmanr (freight against weight); scipy.stats.linregress on log(freight) against log(weight) for slope, R-squared and slope standard error; outliers by the IQR rule (1.5 x IQR, pandas quantile) on Freight per Kg. | rho, slope with 95% interval, R-squared, outlier table (id, value, reason); scatter plot. | Outliers are flagged and explained, never deleted; the log transform is used only for the model, KPI figures stay on raw values; no causal claim.
S7 | Q12 | Supplier on-time rate against the historical rate | purchase_orders: supplier_id, expected_delivery_date, received_date, po_status; suppliers: historical_on_time_rate. | 1,962 valid received POs; S09 (regional distribution centre) is excluded from supplier comparisons, leaving 1,961 rows over S01 to S08 (82 to 563 per supplier, calculated from the source). | scipy.stats.binomtest(k on time, n, p = historical_on_time_rate, two-sided) per supplier; Wilson interval with statsmodels proportion_confint; Holm correction across the 8 suppliers; PO Fill Ratio = SUM(qty_received) / SUM(qty_ordered) on rows with a numeric qty_received. | Actual against historical rate per supplier with interval, p_holm and n; fill ratio table. | The historical rate is a benchmark that may cover another period or measurement; a significant gap is a difference, not a cause.
S8 | Q13 | PO delay distribution and supplier differences | purchase_orders: PO Delay Days = received_date - expected_delivery_date; supplier_id; po_status. | Same 1,962 valid POs (1,961 for supplier comparisons). Rejected orders are excluded from the on-time denominator and reported separately. | pandas describe and quantile (median, IQR, P90); scipy.stats.skew; scipy.stats.kruskal across S01 to S08 with epsilon-squared; pairwise scipy.stats.mannwhitneyu with Holm correction. | Delay histogram, median [IQR] per supplier, status counts (Received, Partially Received, In Transit, Rejected). | Delay is skewed, so rank-based tests are used; the status mix is reported as counts, not as a test.
S9 | Q14 | Actual lead time against the item baseline | purchase_orders: order_date, received_date, item_id; items: baseline_lead_time_days, category. | Received POs with valid order and received dates, item in I001-I030, order_date inside the period (out-of-period rows flagged); categories with at least MIN_N valid POs. | scipy.stats.wilcoxon on the paired difference (actual lead time - baseline) per category; Holm correction across categories; effect size = rank-biserial correlation from the signed ranks. | Median difference in days per category with n and p_holm; bar chart data. | The baseline is a reference value from the items table; the result shows the deviation, not its reason.
S10 | Q15 | Stockout concentration and weekly movement | inventory_daily: date, hospital_id, item_id, unmet_demand_qty; items: criticality. | 8,926 valid hospital-item-days; stockout = unmet_demand_qty > 0 (the source stockout_flag is not used); blank unmet_demand_qty is excluded and counted (the blank share is concentrated in hospital H-C). | scipy.stats.chi2_contingency for hospital x stockout and criticality x stockout with Cramer's V; Wilson intervals per hospital and per criticality; scipy.stats.kendalltau between week number and weekly Stockout Rate; pandas.crosstab to compare the recomputed flag with the source flag. | Stockout Rate with n and interval per hospital and criticality; trend statistic; flag comparison table. | The weekly trend rests on about 13 weekly points (1 January to 31 March 2026), so it is exploratory; no causal claim.
S11 | Q16 | Estimated value of unmet demand and wastage | inventory_daily: unmet_demand_qty, expired_writeoff_qty, damaged_lost_qty; items: unit_cost_egp, category, cold_chain. | Rows with numeric quantities and a valid item cost; Unmet Demand EGP uses items.unit_cost_egp, not the purchase_orders cost column. | pandas groupby and cumulative share (top 10 items); no inferential test, because only 3 of the 30 items are cold-chain items. | Top-10 unmet-demand table, wastage value by category and cold-chain flag. | Values are estimates, not confirmed financial losses.
S12 | Q17 | Treatment delay hours by treatment status | patient_cases: treatment_status, treatment_delay_hours. | Rows with a numeric treatment_delay_hours (5,503 numeric values in the raw table, before duplicate removal; the exact n after cleaning is read from the notebook); "Not given" has no numeric delay values; 14 values equal 999 and 14 are negative (calculated from the source) and are flagged. | scipy.stats.kruskal across statuses with at least MIN_N valid values; pairwise scipy.stats.mannwhitneyu of each status against "Given on time" with Holm correction; median [IQR] and n per status; IQR-rule flag. | Median [IQR] and n per status, test table, box-plot data. | Extreme and negative values are flagged and kept; rank-based tests prevent them from driving the result; delay hours describe timing and do not prove a shortage caused the delay.
S13 | Q18 | Outcomes by treatment status within severity | patient_cases: outcome, treatment_status, severity, icu_admission, complication, length_of_stay_days. | Cases with outcome Died or Recovered (Shortage Mortality = Died / (Died + Recovered)) after removing the 67 fully identical case_id copies; severity after the approved mapping (1/2/3 to Low/Moderate/High), blanks stay NULL; shortage-type = exact match of "Delayed - stock unavailable", "Substitute used", "Not given"; reference group = "Given on time"; "Not given - transferred" is never shortage-type. | scipy.stats.fisher_exact per severity stratum; statsmodels.stats.contingency_tables.StratifiedTable (pooled Mantel-Haenszel odds ratio with 95% interval, Breslow-Day test of equal odds); Wilson intervals for death, ICU and complication shares; scipy.stats.mannwhitneyu for length_of_stay_days. | Death share by severity and treatment status with n; pooled odds ratio adjusted for severity; length-of-stay comparison. | Descriptive association only; the hospital layer is synthetic; results are always read within severity because severity is a confounder; no causal or medical effect is claimed.
S14 | Q19 | Item stockout rate against delayed-stock cases | patient_cases: key_drug_item_id, treatment_status; inventory_daily: item Stockout Rate from S10. | Valid items I001-I030 with at least MIN_N cases (19 valid items in the cases table; the invalid code I000 is excluded). | scipy.stats.spearmanr between the item Stockout Rate and the item share of "Delayed - stock unavailable"; 95% interval with scipy.stats.bootstrap; Wilson interval per item share. | rho, p-value, interval; scatter data per item. | Item-level association with at most 19 points; the hospital-item-day join is not used because repeated inventory keys remain after identical copies are removed; no causal claim.
S15 | Q20 | Shortage-type share by diagnosis and hospital | patient_cases: diagnosis (after the documented mapping to 13 groups, Task 14), hospital_id, treatment_status. | Cases after duplicate removal; hospitals H-A to H-D (the orphan H-E excluded and counted); groups with at least MIN_N cases. | scipy.stats.chi2_contingency for diagnosis x shortage-type and hospital x shortage-type with Cramer's V; adjusted standardized residuals from the expected counts; Wilson intervals; Holm correction on residual p-values. | Shortage-type share with n and interval per diagnosis and hospital; residual table naming groups above or below expectation. | Diagnoses are never merged by visual similarity; shares are descriptive; no causal claim.
S16 | Q21, Q03 | Stability of results after cleaning | Key results of S2 to S15. | Each key test is run twice: on all valid rows and after excluding the flagged rows (Out_of_Period, Invalid_Item, Orphan, Status_Date_Conflict, outlier-flagged values). | Same functions as the original steps; absolute and percentage change of each estimate; change of direction or of significance (p_holm against 0.05). | Stability table linked to the Decision summary table (Q21). | Any change in direction or significance is explained in the Findings and Recommendations (Task 31), not hidden.
S17 | All | Reporting and reproducibility | All results of S0 to S16. | Notebook runs from top to bottom (Restart and Run All) with no manual step. | pandas.DataFrame.to_csv for stats_results.csv; matplotlib savefig for charts; numpy.random.default_rng(42) for every resampling; pip freeze to requirements.txt. | stats_results.csv, chart files and requirements.txt in the python folder of the GitHub repository. | Recalculated KPIs are compared with SQL and Power BI in the Master Reconciliation (Task 29); statistical results feed the Findings and Recommendations (Task 31).