## Gantt
Project Plan - Gantt Chart
ID | Week | Task | Role | Start | End | Deliverable | W1 | W2 | W3 | W4 | W5 | W6 | W7
1 | 1 | KPI Specification and KPIs Document | Hossam - Technical Analytics Lead | 2026-10-11 | 2026-10-15 | KPI Specification + KPIs Document
2 | 1 | GitHub Repository and Branching Strategy | Hossam - Technical Analytics Lead | 2026-10-11 | 2026-10-15 | Repository + Branching Strategy
3 | 1 | Raw and Working Data Layers with Data Profiling | Yahia - Data Preparation & Testing Lead | 2026-10-11 | 2026-10-15 | Raw/Working Data Layers + Profiling Report
4 | 1 | Project Plan and Task Assignment | Yahia - Data Preparation & Testing Lead | 2026-10-11 | 2026-10-15 | Project Plan + Task Assignment & Roles
5 | 1 | Project Proposal | Hossam - Technical Analytics Lead | 2026-10-11 | 2026-10-15 | Project Proposal
6 | 1 | Stakeholder Analysis and User Stories & Use Cases | Ola - Data Quality & Review Lead | 2026-10-11 | 2026-10-15 | Stakeholder Analysis + User Stories & Use Cases
7 | 1 | Literature Review File (Lecturer Input) | Ola - Data Quality & Review Lead | 2026-10-11 | 2026-10-15 | Literature Review
8 | 1 | Data Dictionary | Aya - Data Dictionary & Requirements Lead | 2026-10-11 | 2026-10-15 | Validated Data Dictionary
9 | 1 | Functional & Non-functional Requirements | Aya - Data Dictionary & Requirements Lead | 2026-10-11 | 2026-10-15 | Functional & Non-functional Requirements
10 | 1 | Risk Assessment & Mitigation Plan | Aya - Data Dictionary & Requirements Lead | 2026-10-11 | 2026-10-15 | Risk Assessment & Mitigation Plan
11 | 2 | SQL Staging, Duplicate and Key Integrity Checks | Hossam - Technical Analytics Lead | 2026-10-18 | 2026-10-22 | SQL Staging Layer + Integrity Report
12 | 2 | Shipments Table Cleaning | Yahia - Data Preparation & Testing Lead | 2026-10-18 | 2026-10-22 | Clean Shipments Table + Cleaning Log
13 | 2 | Hospital Tables Cleaning | Yahia - Data Preparation & Testing Lead | 2026-10-18 | 2026-10-22 | Clean Hospital Tables + Cleaning Log
14 | 2 | Data Quality Rules and Mapping Sign-off | Ola - Data Quality & Review Lead | 2026-10-18 | 2026-10-22 | Data Quality Rules + Categorical Mapping Sign-off
15 | 2 | Before/After Reconciliation | Aya - Data Dictionary & Requirements Lead | 2026-10-18 | 2026-10-22 | Before/After Reconciliation Report
16 | 3 | Python Notebook: KPI Recalculation and Basic Charts | Hossam - Technical Analytics Lead | 2026-10-25 | 2026-10-29 | Python Notebook (pandas, matplotlib)
17 | 3 | Derived Fields and Cleaned Dataset | Yahia - Data Preparation & Testing Lead | 2026-10-25 | 2026-10-29 | Derived Fields + Cleaned Dataset
18 | 3 | Question-to-KPI-to-Chart Map | Ola - Data Quality & Review Lead | 2026-10-25 | 2026-10-29 | Analytical Question Map
19 | 3 | Wireframes & UI/UX Guidelines | Aya - Data Dictionary & Requirements Lead | 2026-10-25 | 2026-10-29 | Dashboard UX Specification (Wireframes + Guidelines)
20 | 4 | Software Architecture, DFD and Technology Stack | Hossam - Technical Analytics Lead | 2026-11-01 | 2026-11-05 | Software Architecture + DFD + Technology Stack
21 | 4 | Power BI Data Models (Shipments and Hospitals, Kept Separate) and Core Measures | Yahia - Data Preparation & Testing Lead | 2026-11-01 | 2026-11-05 | Validated Data Models + Core Measures
22 | 4 | Problem Statement and Use Case Diagram | Ola - Data Quality & Review Lead | 2026-11-01 | 2026-11-05 | Problem Statement + Use Case Diagram
23 | 4 | ER Diagram and Logical & Physical Schema | Aya - Data Dictionary & Requirements Lead | 2026-11-01 | 2026-11-05 | ER Diagram + Logical & Physical Schema
24 | 5 | Dashboard Page 1: Executive Overview | Ola - Data Quality & Review Lead | 2026-11-08 | 2026-11-12 | Dashboard Page 1
25 | 5 | Dashboard Page 2: Delivery & Cycle Time | Hossam - Technical Analytics Lead | 2026-11-08 | 2026-11-12 | Dashboard Page 2
26 | 5 | Dashboard Page 3: Suppliers & Cost | Aya - Data Dictionary & Requirements Lead | 2026-11-08 | 2026-11-12 | Dashboard Page 3
27 | 5 | Dashboard Page 4: Purchase Orders & Inventory | Yahia - Data Preparation & Testing Lead | 2026-11-08 | 2026-11-12 | Dashboard Page 4
28 | 5 | Dashboard Page 5: Case Impact & Decision Quality | Hossam - Technical Analytics Lead | 2026-11-08 | 2026-11-12 | Dashboard Page 5
29 | 6 | Master Reconciliation (SQL, Python, Power BI) | Hossam - Technical Analytics Lead | 2026-11-15 | 2026-11-19 | Master Reconciliation Report
30 | 6 | Test Plan, Functional Testing, UAT and Bug Log | Yahia - Data Preparation & Testing Lead | 2026-11-15 | 2026-11-19 | Test Plan + Dashboard Functional Test + UAT & Bug Log
31 | 6 | Findings and Recommendations | Ola - Data Quality & Review Lead | 2026-11-15 | 2026-11-19 | Findings & Recommendations
32 | 6 | README and Execution Guide | Aya - Data Dictionary & Requirements Lead | 2026-11-15 | 2026-11-19 | README + Execution Guide
33 | 7 | Technical Sign-off and Final Refresh QA | Hossam - Technical Analytics Lead | 2026-11-22 | 2026-11-26 | Technical Sign-off Package + Final Refresh QA
34 | 7 | Project Infographic (Single 16:9 Image) | Yahia - Data Preparation & Testing Lead | 2026-11-22 | 2026-11-26 | Project Infographic
35 | 7 | Project Presentation (PPT/PDF) | Ola - Data Quality & Review Lead | 2026-11-22 | 2026-11-26 | Project Presentation
36 | 7 | User Manual and Final Documentation | Aya - Data Dictionary & Requirements Lead | 2026-11-22 | 2026-11-26 | User Manual + Final Documentation

## Milestones
Project Plan - Milestones
Milestone | Date | Focus | Exit Gate
Week 1 end | 2026-10-15 | Scope, Definitions, Raw/Working Layers and Planning Documents | Planning, literature review and requirements documents are ready for submission on 16 October 2026.
Week 2 end | 2026-10-22 | Data Cleaning, Integrity Checks and Quality Rules | Cleaning logs and documented mappings are delivered; before/after differences are explained.
Week 3 end | 2026-10-29 | Derived Fields, Cleaned Dataset, Python Notebook and Dashboard Design | Derived fields are validated and the analytical question map is agreed.
Week 4 end | 2026-11-05 | System Analysis & Design Pack and Power BI Data Models | Design documents are ready for submission on 6 November 2026; relationships, denominators and filters are tested.
Week 5 end | 2026-11-12 | Dashboard Build: Five Pages | Every visual is linked to a specific question, column and KPI.
Week 6 end | 2026-11-19 | Reconciliation, Testing, UAT and Findings | No critical error remains open.
Week 7 end | 2026-11-26 | Sign-off, Infographic, Presentation and Final Documentation | Final internal delivery.
DEPI Submission | Date | Item
DEPI submission | 2026-10-16 | Project Planning & Management | Documents uploaded to GitHub
DEPI submission | 2026-10-16 | Literature Review | Documents uploaded to GitHub
DEPI submission | 2026-10-16 | Requirements Gathering | Documents uploaded to GitHub
DEPI submission | 2026-11-06 | System Analysis & Design | Documents uploaded to GitHub
DEPI submission | 2026-11-30 | Implementation (Source Code & Execution) | Documents uploaded to GitHub
DEPI submission | 2026-12-04 | Final Presentation, Testing & Reports | Documents uploaded to GitHub
Internal final delivery | 2026-11-26 | Final internal delivery (Week 7 end) | Final internal delivery

## Deliverables
Project Plan - Deliverables
Task ID | Deliverable | Role | Week | Due Date
1 | KPI Specification + KPIs Document | Hossam - Technical Analytics Lead | 1 | 2026-10-15
2 | Repository + Branching Strategy | Hossam - Technical Analytics Lead | 1 | 2026-10-15
3 | Raw/Working Data Layers + Profiling Report | Yahia - Data Preparation & Testing Lead | 1 | 2026-10-15
4 | Project Plan + Task Assignment & Roles | Yahia - Data Preparation & Testing Lead | 1 | 2026-10-15
5 | Project Proposal | Hossam - Technical Analytics Lead | 1 | 2026-10-15
6 | Stakeholder Analysis + User Stories & Use Cases | Ola - Data Quality & Review Lead | 1 | 2026-10-15
7 | Literature Review | Ola - Data Quality & Review Lead | 1 | 2026-10-15
8 | Validated Data Dictionary | Aya - Data Dictionary & Requirements Lead | 1 | 2026-10-15
9 | Functional & Non-functional Requirements | Aya - Data Dictionary & Requirements Lead | 1 | 2026-10-15
10 | Risk Assessment & Mitigation Plan | Aya - Data Dictionary & Requirements Lead | 1 | 2026-10-15
11 | SQL Staging Layer + Integrity Report | Hossam - Technical Analytics Lead | 2 | 2026-10-22
12 | Clean Shipments Table + Cleaning Log | Yahia - Data Preparation & Testing Lead | 2 | 2026-10-22
13 | Clean Hospital Tables + Cleaning Log | Yahia - Data Preparation & Testing Lead | 2 | 2026-10-22
14 | Data Quality Rules + Categorical Mapping Sign-off | Ola - Data Quality & Review Lead | 2 | 2026-10-22
15 | Before/After Reconciliation Report | Aya - Data Dictionary & Requirements Lead | 2 | 2026-10-22
16 | Python Notebook (pandas, matplotlib) | Hossam - Technical Analytics Lead | 3 | 2026-10-29
17 | Derived Fields + Cleaned Dataset | Yahia - Data Preparation & Testing Lead | 3 | 2026-10-29
18 | Analytical Question Map | Ola - Data Quality & Review Lead | 3 | 2026-10-29
19 | Dashboard UX Specification (Wireframes + Guidelines) | Aya - Data Dictionary & Requirements Lead | 3 | 2026-10-29
20 | Software Architecture + DFD + Technology Stack | Hossam - Technical Analytics Lead | 4 | 2026-11-05
21 | Validated Data Models + Core Measures | Yahia - Data Preparation & Testing Lead | 4 | 2026-11-05
22 | Problem Statement + Use Case Diagram | Ola - Data Quality & Review Lead | 4 | 2026-11-05
23 | ER Diagram + Logical & Physical Schema | Aya - Data Dictionary & Requirements Lead | 4 | 2026-11-05
24 | Dashboard Page 1 | Ola - Data Quality & Review Lead | 5 | 2026-11-12
25 | Dashboard Page 2 | Hossam - Technical Analytics Lead | 5 | 2026-11-12
26 | Dashboard Page 3 | Aya - Data Dictionary & Requirements Lead | 5 | 2026-11-12
27 | Dashboard Page 4 | Yahia - Data Preparation & Testing Lead | 5 | 2026-11-12
28 | Dashboard Page 5 | Hossam - Technical Analytics Lead | 5 | 2026-11-12
29 | Master Reconciliation Report | Hossam - Technical Analytics Lead | 6 | 2026-11-19
30 | Test Plan + Dashboard Functional Test + UAT & Bug Log | Yahia - Data Preparation & Testing Lead | 6 | 2026-11-19
31 | Findings & Recommendations | Ola - Data Quality & Review Lead | 6 | 2026-11-19
32 | README + Execution Guide | Aya - Data Dictionary & Requirements Lead | 6 | 2026-11-19
33 | Technical Sign-off Package + Final Refresh QA | Hossam - Technical Analytics Lead | 7 | 2026-11-26
34 | Project Infographic | Yahia - Data Preparation & Testing Lead | 7 | 2026-11-26
35 | Project Presentation | Ola - Data Quality & Review Lead | 7 | 2026-11-26
36 | User Manual + Final Documentation | Aya - Data Dictionary & Requirements Lead | 7 | 2026-11-26

## Resource Allocation
Project Plan - Resource Allocation
Role | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Total Tasks
Hossam - Technical Analytics Lead | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 10
Yahia - Data Preparation & Testing Lead | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 9
Ola - Data Quality & Review Lead | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 8
Aya - Data Dictionary & Requirements Lead | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 9
Total | 10 | 5 | 4 | 4 | 5 | 4 | 4 | 36
Role | Responsibilities
Hossam - Technical Analytics Lead | Project proposal; KPI specification and KPIs document; GitHub repository; SQL staging and integrity checks; Python notebook (KPI recalculation and basic charts); software architecture, DFD and technology stack; dashboard Pages 2 (Delivery & Cycle Time) and 5 (Case Impact & Decision Quality); master reconciliation; technical sign-off and final refresh QA.
Yahia - Data Preparation & Testing Lead | Raw and Working data layers with profiling; project plan and task assignment; cleaning of the shipments and hospital tables; derived fields and cleaned dataset; Power BI data models and core measures; dashboard Page 4 (Purchase Orders & Inventory); test plan, UAT and bug log; project infographic.
Ola - Data Quality & Review Lead | Stakeholder analysis, user stories and use cases; literature review file; data quality rules and mapping sign-off; analytical question map; problem statement and use case diagram; dashboard Page 1 (Executive Overview); findings and recommendations; project presentation.
Aya - Data Dictionary & Requirements Lead | Data dictionary; functional and non-functional requirements; risk assessment; before/after reconciliation; wireframes and UI/UX guidelines; ER diagram and logical & physical schema; dashboard Page 3 (Suppliers & Cost); README and execution guide; user manual and final documentation.