## Roles
Task Assignment & Roles
Team Member and Role | Responsibilities | Number of Tasks
Hossam - Technical Analytics Lead | Project proposal; KPI specification and KPIs document; GitHub repository; SQL staging and integrity checks; Python notebook (KPI recalculation and basic charts); software architecture, DFD and technology stack; dashboard Pages 2 (Delivery & Cycle Time) and 5 (Case Impact & Decision Quality); master reconciliation; technical sign-off and final refresh QA. | 10
Yahia - Data Preparation & Testing Lead | Raw and Working data layers with profiling; project plan and task assignment; cleaning of the shipments and hospital tables; derived fields and cleaned dataset; Power BI data models and core measures; dashboard Page 4 (Purchase Orders & Inventory); test plan, UAT and bug log; project infographic. | 9
Ola - Data Quality & Review Lead | Stakeholder analysis, user stories and use cases; literature review file; data quality rules and mapping sign-off; analytical question map; problem statement and use case diagram; dashboard Page 1 (Executive Overview); findings and recommendations; project presentation. | 8
Aya - Data Dictionary & Requirements Lead | Data dictionary; functional and non-functional requirements; risk assessment; before/after reconciliation; wireframes and UI/UX guidelines; ER diagram and logical & physical schema; dashboard Page 3 (Suppliers & Cost); README and execution guide; user manual and final documentation. | 9
Total |  | 36

## Tasks
Task Assignment
Task ID | Week | Task | Responsible Role | Start | End | Deliverable
1 | 1 | KPI Specification and KPIs Document | Hossam - Technical Analytics Lead | 2026-10-11 | 2026-10-15 | KPI Specification + KPIs Document
2 | 1 | GitHub Repository and Branching Strategy | Hossam - Technical Analytics Lead | 2026-10-11 | 2026-10-15 | Repository + Branching Strategy
3 | 1 | Raw and Working Data Layers with Data Profiling | Yahia - Data Preparation & Testing Lead | 2026-10-11 | 2026-10-15 | Raw/Working Data Layers + Profiling Report
4 | 1 | Project Plan and Task Assignment | Yahia - Data Preparation & Testing Lead | 2026-10-11 | 2026-10-15 | Project Plan + Task Assignment & Roles
5 | 1 | Project Proposal | Hossam - Technical Analytics Lead | 2026-10-11 | 2026-10-15 | Project Proposal
6 | 1 | Stakeholder Analysis and User Stories & Use Cases | Ola - Data Quality & Review Lead | 2026-10-11 | 2026-10-15 | Stakeholder Analysis + User Stories & Use Cases
7 | 1 | Literature Review File (Lecturer Input) | Ola - Data Quality & Review Lead | 2026-10-11 | 2026-10-15 | Literature Review
8 | 1 | Data Dictionary | Aya - Data Dictionary & Requirements Lead | 2026-10-11 | 2026-10-15 | Validated Data Dictionary
9 | 1 | Functional & Non-functional Requirements | Aya - Data Dictionary & Requirements Lead | 2026-10-11 | 2026-10-15 | Functional & Non-functional Requirements
10 | 1 | Risk Assessment & Mitigation Plan | Aya - Data Dictionary & Requirements Lead | 2026-10-11 | 2026-10-15 | Risk Assessment & Mitigation Plan
11 | 2 | SQL Staging, Duplicate and Key Integrity Checks | Hossam - Technical Analytics Lead | 2026-10-18 | 2026-10-22 | SQL Staging Layer + Integrity Report
12 | 2 | Shipments Table Cleaning | Yahia - Data Preparation & Testing Lead | 2026-10-18 | 2026-10-22 | Clean Shipments Table + Cleaning Log
13 | 2 | Hospital Tables Cleaning | Yahia - Data Preparation & Testing Lead | 2026-10-18 | 2026-10-22 | Clean Hospital Tables + Cleaning Log
14 | 2 | Data Quality Rules and Mapping Sign-off | Ola - Data Quality & Review Lead | 2026-10-18 | 2026-10-22 | Data Quality Rules + Categorical Mapping Sign-off
15 | 2 | Before/After Reconciliation | Aya - Data Dictionary & Requirements Lead | 2026-10-18 | 2026-10-22 | Before/After Reconciliation Report
16 | 3 | Python Notebook: KPI Recalculation and Basic Charts | Hossam - Technical Analytics Lead | 2026-10-25 | 2026-10-29 | Python Notebook (pandas, matplotlib)
17 | 3 | Derived Fields and Cleaned Dataset | Yahia - Data Preparation & Testing Lead | 2026-10-25 | 2026-10-29 | Derived Fields + Cleaned Dataset
18 | 3 | Question-to-KPI-to-Chart Map | Ola - Data Quality & Review Lead | 2026-10-25 | 2026-10-29 | Analytical Question Map
19 | 3 | Wireframes & UI/UX Guidelines | Aya - Data Dictionary & Requirements Lead | 2026-10-25 | 2026-10-29 | Dashboard UX Specification (Wireframes + Guidelines)
20 | 4 | Software Architecture, DFD and Technology Stack | Hossam - Technical Analytics Lead | 2026-11-01 | 2026-11-05 | Software Architecture + DFD + Technology Stack
21 | 4 | Power BI Data Models (Shipments and Hospitals, Kept Separate) and Core Measures | Yahia - Data Preparation & Testing Lead | 2026-11-01 | 2026-11-05 | Validated Data Models + Core Measures
22 | 4 | Problem Statement and Use Case Diagram | Ola - Data Quality & Review Lead | 2026-11-01 | 2026-11-05 | Problem Statement + Use Case Diagram
23 | 4 | ER Diagram and Logical & Physical Schema | Aya - Data Dictionary & Requirements Lead | 2026-11-01 | 2026-11-05 | ER Diagram + Logical & Physical Schema
24 | 5 | Dashboard Page 1: Executive Overview | Ola - Data Quality & Review Lead | 2026-11-08 | 2026-11-12 | Dashboard Page 1
25 | 5 | Dashboard Page 2: Delivery & Cycle Time | Hossam - Technical Analytics Lead | 2026-11-08 | 2026-11-12 | Dashboard Page 2
26 | 5 | Dashboard Page 3: Suppliers & Cost | Aya - Data Dictionary & Requirements Lead | 2026-11-08 | 2026-11-12 | Dashboard Page 3
27 | 5 | Dashboard Page 4: Purchase Orders & Inventory | Yahia - Data Preparation & Testing Lead | 2026-11-08 | 2026-11-12 | Dashboard Page 4
28 | 5 | Dashboard Page 5: Case Impact & Decision Quality | Hossam - Technical Analytics Lead | 2026-11-08 | 2026-11-12 | Dashboard Page 5
29 | 6 | Master Reconciliation (SQL, Python, Power BI) | Hossam - Technical Analytics Lead | 2026-11-15 | 2026-11-19 | Master Reconciliation Report
30 | 6 | Test Plan, Functional Testing, UAT and Bug Log | Yahia - Data Preparation & Testing Lead | 2026-11-15 | 2026-11-19 | Test Plan + Dashboard Functional Test + UAT & Bug Log
31 | 6 | Findings and Recommendations | Ola - Data Quality & Review Lead | 2026-11-15 | 2026-11-19 | Findings & Recommendations
32 | 6 | README and Execution Guide | Aya - Data Dictionary & Requirements Lead | 2026-11-15 | 2026-11-19 | README + Execution Guide
33 | 7 | Technical Sign-off and Final Refresh QA | Hossam - Technical Analytics Lead | 2026-11-22 | 2026-11-26 | Technical Sign-off Package + Final Refresh QA
34 | 7 | Project Infographic (Single 16:9 Image) | Yahia - Data Preparation & Testing Lead | 2026-11-22 | 2026-11-26 | Project Infographic
35 | 7 | Project Presentation (PPT/PDF) | Ola - Data Quality & Review Lead | 2026-11-22 | 2026-11-26 | Project Presentation
36 | 7 | User Manual and Final Documentation | Aya - Data Dictionary & Requirements Lead | 2026-11-22 | 2026-11-26 | User Manual + Final Documentation

## Role-Week Matrix
Task Count by Role and Week
Role | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Total
Hossam - Technical Analytics Lead | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 10
Yahia - Data Preparation & Testing Lead | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 9
Ola - Data Quality & Review Lead | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 8
Aya - Data Dictionary & Requirements Lead | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 9